## Sheet1
PHASE | DATE | HIGHLIGHTS | TOPICS TO BE DISCUSSED IN THE NEXT MEET | NEXT MEET | DURATION | % OF WORK COMPLETED
PLANNING | 4TH SEP | assigning works, understanding per chart | uml diagrams, project structure | 9TH SEP | 2 hrs | 1
PLANNING | 9TH SEP | brainstorming the project idea | understanding the risks in the project | 11TH SEP | 3 hrs | 2
PLANNING | 11TH SEP | pert and gantt chart, effort estimates | finalizing the project plan | 12TH SEP | 3 hrs | 3
REQUIREMENT & ANALYSIS | 12TH SEP | collecting the information related to the project | gathering the requirements | 13TH SEP | 5 hrs | 6
REQUIREMENT & ANALYSIS | 13TH SEP | functional and non-functional requirements | finalizing the requirements | 19TH SEP | 4 hrs | 10
REQUIREMENT & ANALYSIS | 19TH SEP | adding additional requirements | construction of system architecture | 20TH SEP | 4 hrs | 11
DESGIN | 20TH SEP | understanding of UML diagrams | construction of UML diagrams | 24TH SEP | 3 hrs | 14
DESGIN | 24TH SEP | construction of use case diagrams,class diagram | construction of sequence diagrams | 25TH SEP | 4 hrs | 16
DESGIN | 25TH SEP | construction of class diagram,sequence diagram | Updating the project plan | 26TH SEP | 4 hrs | 20