## Sheet1
PHASE | DATE | HIGHLIGHTS | TOPICS TO BE DISCUSSED IN THE NEXT MEET | NEXT MEET | DURATION | % OF WORK COMPLETED
PLANNING | 4TH SEP | assigning works, understanding per chart | uml diagrams, project structure | 9TH SEP | 2 hrs | 1
PLANNING | 9TH SEP | brainstorming the project idea | understanding the risks in the project | 11TH SEP | 3 hrs | 2
PLANNING | 11TH SEP | pert and gantt chart, effort estimates | finalizing the project plan | 12TH SEP | 3 hrs | 3
REQUIREMENT & ANALYSIS | 12TH SEP | collecting the information related to the project | gathering the requirements | 13TH SEP | 5 hrs | 6
REQUIREMENT & ANALYSIS | 13TH SEP | functional and non-functional requirements | finalizing the requirements | 19TH SEP | 4 hrs | 10
REQUIREMENT & ANALYSIS | 19TH SEP | adding additional requirements | construction of system architecture | 20TH SEP | 4 hrs | 11
DESGIN | 20TH SEP | understanding of UML diagrams | construction of UML diagrams | 24TH SEP | 3 hrs | 14
DESGIN | 24TH SEP | construction of use case diagrams,class diagram | construction of sequence diagrams | 25TH SEP | 4 hrs | 16
DESGIN | 25TH SEP | construction of class diagram,sequence diagram | Updating the project plan | 26TH SEP | 4 hrs | 20
CODE | 1ST OCT | INSTALLING SOFTWARES | CONTINUATION | 3RD OCT | 3 hrs | 21
CODE | 3RD OCT | INSTALLING SOFTWARES | OUTLINING THE CODE | 6TH OCT | 3 hrs | 22
CODE | 6TH OCT | OUTLINING THE CODE | OUTLINING THE CODE | 7TH OCT | 4 hrs | 23
CODE | 7Th OCT | Writing basic code | writing the code | 9th OCT | 4hrs | 30
CODE | 8TH OCT | Writing basic code | writing the code module | 10th OCT | 5 hrs | 35
CODE | 10TH OCT | wrting the code for admin module | writing the code for admin module | 13th OCT | 4hrs | 38
CODE | 13TH OCT | Writing the code for admin module | writing the code for admin module | 16th OCT | 4hrs | 42
CODE | 16th OCT | Writing the code for admin module | checking the writen code module | 18th OCT | 5hrs | 50
CODE | 18th OCT | verfying the code logic | writing the functionalties of user module | 21th OCT | 3hrs | 52
CODE | 21ST OCT | writing the code for user module | writing the code for user module | 23RD OCT | 4hrs | 54
CODE | 23RD OCT | writing the code for user module | writing the code for user module | 25THOCT | 3hrs | 55
CODE | 25TH OCT | writing the code for user module | writing the code for user module | 26TH OCT | 3hrs | 58
CODE | 26TH OCT | writing the code for user module | writing the code for user module | 28TH OCT | 3hrs | 59
CODE | 28TH OCT | writing the code for user module | writing the code for user module | 29TH OCT | 4hrs | 63
CODE | 29TH OCT | writing the code for user module | verifying the code written for user module | 30TH OCT | 3hrs | 65
CODE | 30TH OCT | Writing the code for doctor module | writing the code for doctor module | 1ST NOV | 4hrs | 66
CODE | 1ST NOV | Writing the code for doctor module | writing the code for doctor module | 2ND NOV | 3hrs | 68
CODE | 2ND NOV | Writing the code for doctor module | writing the code for doctor module | 4TH NOV | 2hrs | 70
CODE | 4TH NOV | Writing the code for doctor module | verifying the code written for doctor module | 5TH NOV | 3hrs | 71
CODE | 5TH NOV | Writng the code for hospital module | Writng the code for hospital module | 7TH NOV | 3hrs | 74
CODE | 7TH NOV | Writng the code for hospital module | Writng the code for hospital module | 8TH NOV | 4hrs | 76
CODE | 8TH NOV | Writng the code for hospital module | verifying the code written for hospital module | 9TH NOV | 2hrs | 78
CODE | 9th NOV | Writng the code for Pharmacy module | Writng the code for Pharmacy module | 10TH NOV | 3hrs | 79
CODE | 10TH NOV | Writng the code for Pharmacy module | verifying the code written for pharmacy module | 11TH NOV | 2hrs | 80
TESTING | 11th NOV | Testing the project | Testing the project | 12th NOV | 4hrs | 84
TESTING | 12th NOV | Testing the project | Testing the project | 13th NOV | 3hrs | 87
TESTING | 13th NOV | Testing the project | Testing the project | 14th NOV | 3hrs | 89
TESTING | 14th NOV | Testing the project | Testing the project | 15th NOV | 2hrs | 94
TESTING | 15th NOV | Testing the project | Final documentation | 16th NOV | 3hrs | 96
TESTING | 16th NOV | Final documentation |  | 17th NOV | 2hrs | 100